## Sheet1
Task ID | Task Name | Assigned | Task Status | Exepected Time To Finish | Actual Time To Finish
1 | MCAL_DIO_DESIGN | Bassel Yasser | 100 | 30 minutes | 1 hour
2 | MCAL_DIO_IMPLEMENTATION | Bassel Yasser | 100 | 1 hour | 1.5 hour
3 | MCAL_DIO_TESTING | Bassel Yasser | 100 | 15 minutes | 15 minutes
4 | ECU_LCD_DESIGN | Bassel Yasser | 100 | 30 minutes | 20 minutes
5 | ECU_LCD_IMPLEMENTATION | Bassel Yasser | 100 | 45 minutes | 1 hour
6 | ECU_LCD_TESTING | Bassel Yasser | 100 | 30 minutes | 15 minutes
7 | ECU_KEYPAD_DESIGN | Sharpel Malak | 100 | 30 minutes | 15 minutes
8 | ECU_KEYPAD_IMPLEMENTATION | Sharpel Malak | 100 | 30 minutes | 45 minutes
9 | ECU_KEYPAD_TESTING | Sharpel Malak | 100 | 15 minutes | 15 minutes
10 | MCAL_ADC_DESIGN | Sherif Ashraf | 100 | 30 minutes | 30 minutes
11 | MCAL_ADC_IMPLEMENTATION | Sherif Ashraf | 100 | 2 hours | 2 hours
12 | MCAL_ADC_TESTING | Sherif Ashraf | 100 | 45 minutes | 30 minutes
13 | MCAL_TIMER_DESIGN | Alaa Hisham | 100 | 15 minutes | 15 minutes
14 | MCAL_TIMER_IMPLEMENTATION | Alaa Hisham | 100 | 15 minutes | 15 minutes
15 | MCAL_TIMER_TESTING | Alaa Hisham | 100 | 15 minutes | 1 hour
16 | ECU_BUZZER_DESIGN | Alaa Hisham | 100 | 15 minutes | 15 minutes
17 | ECU_BUZZER_IMPLEMENTATION | Alaa Hisham | 100 | 15 minutes | 15 minutes
18 | ECU_BUZZER_TESTING | Alaa Hisham | 100 | 15 minutes | 15 minutes
19 | ECU_TEMPSENSOR_DESIGN | Alaa Hisham | 100 | 15 minutes | 15 minutes
20 | ECU_TEMPSENSOR_IMPLEMENTATION | Alaa Hisham | 100 | 30 minutes | 30 minutes
21 | ECU_TEMPSENSOR_TESTING | Alaa Hisham | 100 | 15 minutes | 30 minutes
22 | APP_DESIGN | Alaa Hisham | 100 | 30 minutes | 30 minutes
23 | APP_IMPLEMENTATION | Alaa Hisham | 100 | 2 hours | 3 hours
24 | APP_TESTING | team | 100 | 4 hours | 10 hours
25 | Documentation | team | 100 | 2 hours | 3 hours
26 | Integrate all Drivers | team | 100 | 1 hour | 110 minutes